## 00 Introduction
Introduction & Objectives
To efficiently track project progress and to ensure final objectives are met through preventive and corrective actions, TIC projects are recommended to establish a M&E framework including metrics composed of baselines, output/outcome results and indicators for each of the seven result levels (see Result Staircase to the right). The purpose of the TIC Metrics is to serve as an aid to TIC project teams in establishing and measuring the progress, outcome and impact of their transformational projects from the point of entry to project completion and beyond. Steps to complete the TIC Metrics Framework: 1) Familiarize yourself with the TIC Metrics Framework by reading this Introduction sheet and consult the TIC Metrics Guideline as required. The guideline includes detailed information on the framework including resources such as commonly used terms, examples of KPIs, checklists and references. 2) Complete the Theory of Change template (planning tool) When: upfront for the proposal 3) Complete the TIC Metrics Template (tracking project progress and impact tool) When: Upfront or near the beginning of the project 3a) Develop results and indicators for each of the results steps - plot them in the appropriate sections of the TIC Metrics Template 3b) Develop baselines for the 3 main result levels (Output, Outcome, Impact) using the indicators and qualitative observations - plot them in the appropriate sections of the TIC Metrics Template. 4) Complete the Monitoring LogFrame Template (detailed tracking and monitoring tool) When: first 6 month of the project (team in place) 4) Work backwards and forwards through the models to validate the logic of sequences - ensure relation between indicators, targets and baselines. |  |  |  | Result Staircase
The TIC Metrics Framework
The TIC Metrics Framework consist of four components: the Result Staircase the Theory of Change Template, the Metrics Template and the Monitoring LogFrame. The models are described below and the templates including examples are available as separate sheets within this document (Template sheets are green, Examples are blue). Examples are provided per TIC project cluster 1. The Theory of Change The purpose of the Theory of Change model is to develop the project's basic rational and logical framework to ensure a plausible relation between inputs and impact. Theory of Change is essentially a comprehensive description and illustration of how and why a desired change is expected to happen in a particular context. It is particularly focused on mapping out or “filling in” what has been described as the “missing middle” between what a project or change initiative does (its activities or interventions) and how these lead to desired goals being achieved. It does this by first identifying the desired long-term goals and then works back from these to identify all the conditions (outcomes) that must be in place (and how these related to one another causally) for the goals to occur. 2. The Result Staircase The purpose of the result staircase is to provide a model enabling projects to be able to focus on specific targets at any given point while maintaining a complete overview of how project activities, outputs, outcomes and impact are interlinked and continuously affect one another. There are numerous levels at which project impact can be achieved. These levels of effect are illustrated using the results staircase, step 1-7. A project offers certain services and products. These are "Outputs". Because of these outputs, results are produced within the target groups. These are "Outcomes". These outcomes can be of various kinds may provide results at the society level. These are "Impact".
Result Level |  | Step | When | Description
OUTPUT (project) | Output Level - Targets and Indicators | 1 | Activities are carried out by the project within its lifespan | Impact and outcomes result from the products produced or services provided by a project. These products or services are Outputs. They are not themselves results; they are prerequisites for achieving results on higher levels (outcomes and Impact).
|  | 2 | The target groups are reached (service or product received)
|  | 3 | The target groups accepts the offer (service or product). Level 3 is considered a bridge to outcomes.
OUTCOME (Target group) | Result Level - Target and Indicators | 4 | The outcome level is reached when we observe changes in attitudes and/or knowledge and skill levels within the target group | Results within the target group are Outcomes. What benefits does the project have for the target group, and what changes is it intended to bring about? Outcomes always refer to results within the project target group and can be further divided, as seen at levels 4 - 6 in the result staircase (and to the left). Successful outcomes will contribute to changes at the intervention/societal level. Projects can have multiple outcomes addressing the same desired change (the final goal).
|  | 5 | The outcome level is reached when we observe changes in behavior within the target group
|  | 6 | The outcome level is reached when the target group's circumstances change, and members are able to improve their living conditions.
IMPACT (Society) | Result Level - Target and Indicators | 7 | The outcome level is reached when larger populations are affected by the changes driven by the project (social, economic, etc.) | Results at the intervention/societal level are "impact" (as shorthand for social impact). Impact describe the long-term results that are achieved or influenced by the project. These societal-level objectives are closely linked to the organization’s vision. Impact always relates to a part of the society as a whole, for instance the population in the district of a city or within a specific region. TIC projects are to develop targets and indicators for long term impact and include the responsibility of monitoring and reporting in TIC Completion Report (Transition to Business as Usual section) upon project accomplishment.
3. The TIC Metrics The purpose of the TIC Metrics is to provide a model enabling TIC projects to identify and track project targets and impact through use of baselines and indicators. Following the logic of the Result Staircase; "Results" and "Indicators" as well as their "Baselines" and "Targets" are developed for each of the three main result levels (Output, Outcome and Impact) by using the TIC Metrics Template. For Large-Scale Projects, results and indicators are further categorized as per the seven result levels of the Result Staircase. It is recommended to first develop the Results and Indicators e.g., what you want to achive and what you would like to measure, and subsequently develop the baselines (initial values of the indicators) and the targets (desired values at a certain point e.g., at gate 1, end of year, end of project). The TIC Metrics Template depicts the logic of your Theory of Change model and the results staircase in which input is found at the bottom, impact at top. The same logic holds for the TIC Metrics Template where outputs are defined on the left side and impact on the right. Each step (from left to right-top down) is based on the one preceding it. The model is flexible and approached in multiple directions e.g. right-left/bottom-top (working backward approach) and subsequently for plausibility check left-right/top-down to ensure a logic and impact oriented approach. The focus here is on the if-then relationships between the individual steps - If you succeed in moving to the end in both directions without mishap, you have a logical impact metrics model.
Plausibility Check – from inputs to impact
Level 1 | If the necessary resources (inputs) are available, the planned activities can begin and the offerings or products can be created
Level 2 | If the offerings and the products are available, they can be used by the target group
Level 3 | If the offerings and the products are used, then the prerequisite for participant satisfaction is met
Level 4 | If the participants are satisfied with the offering, then the prerequisite has been met for the desired changes in target-group knowledge and attitudes to be effected
Level 5 | If the desired changes in target-group knowledge and attitudes have been effected, this creates the possibility that they will act differently
Level 6 | If members of the target group act differently, then their living conditions may change
Level 7 | If participants’ living conditions change, then this contributes to changes at the societal level
4. The Monitoring LogFrame The purpose of the Monitoring LogFrame is to provide TIC teams with a standard template to systematically track and monitor project progress on regular basis (weekly, monthly, quarterly). The tool is used by project teams to collect, manage and analyse information in order to update the TIC Metrics, and to inform preventive and corrective measures. The tool provides the ability to extract trends over time for each of the indicators and against comparators (baseline, target), details on what data collection tools are to be used on each indicator, calculation methods, frequency, etc.
Points to consider before getting started
1. Develop a clear problem analysis at the baseline, explaining what the problem to be addressed is and how its root causes are considered in the development of the project strategy.
2. It is recommende to first develop the project results at the Output/Outcome/Impact levels, then their indicators and targets, and finally the baselines.
3. Developing solid baselines to measure against is essential for a strong M&E framework. Baseline data is developed from the same indicators used to track future results. Baselines may be supported by qualitative obseevations and testimonials.
4. When developing indicators, consider carefully what you would like to measure. A few complementary indicators for each result step are in most cases sufficient
5. Indicators are not carved in stone and should be reviewed frequently to ensure alignment with the projects progress and desired impact
6. Establishing precise indicators can be challenging but everything is measurable. It is better to have indicators based on quality assumptions or proxi indicators than having no indicators
7. Indicators and their baseline and target values should be developed in collaboration with project stakeholders
8. The TIC Metrics Framework is based on a people centered approach where results and indicators are based on behavioral change. It is therefore advised to formulate results and indicators according to the change in the target group(s) e.g. Patients, MSF staff, health workers.

## Theory of Change
Theory of Change Template - Defining Project Logic - Large / Very-Large Scale
Defining goals and the path to reach them
1a | 1b | 1c | 3c | 3b | 3a | 2 | Recommended order to complete: Step 1: Team first defines: (a) the problem the team is solving, (b) who is the target audience and (c) how they would reach that audience. Step 2: The team then develops their long-term vision for change - focus on the goal, then work backwards" Step 3: The team then works backwards from the vision to: (a) define benefits / project outcomes of the work (b) define services or products / project outputs (c) define activities that are needed to bring about change
What problem we are trying to solve? | Who is our key audience? | What is your entry point to reach your audience? | What steps or activities are needed to generate the services or products? | What are the services and products leading to those benefits/ outcomes? (Project outputs)? | What are the wider benefits of your work (Project outcomes)? | What is the long-term change you see as your goal (Project impact)?
Key Assumptions:
What is the problem / issue with the situation today that is critical enough to merit investment in the project; describe the scale and scope of the problem? | Who are the target audiences (may be multiple audiences)? | How will the project reach those audiences? | What type of activities or interventions will lead to the outputs and outcomes identified as preconditions for achieving the output and then outcomes? | What are the outputs (results) that are measurable, specific/ tangible enough to understand what the product or change would be exactly about? | What are clear benefits for the target groups? | Identify the desired long-term goals / vision; should be clear, realistic and definite.
Source: Capgemini Transformaion
Step 1
Step 3
Step 2

## Metrics Template
Transformational Investment Capacity Project Metrics Framework - LARGE SCALE
Project Name:
Problem Statement:
Project Objective:
Target Groups (users)
Development/revision date:
Project Baseline
Output Baseline |  |  | Outcome Baseline |  |  | Impact Baseline
Outputs (Results of project activities) |  |  | Outcomes (results of project outputs) |  |  | Impact (Results of project outcomes when scaled)
Offerings |  |  | Results at the Target Group Level |  |  | Results at the Intervention/Societal Level
RESULTS What you do or offer in your project (and the people you reach) | INDICATORS | TARGETS | RESULTS (What you want the project to achieve within your target groups) | INDICATORS | TARGETS | The contribution you want to make with the project at the societal level | INDICATORS/PROXIES | TARGETS
| Quantitative |  |  | Quantitative |  |  | Quantitative
1) Output | 1) Indicator | 1) Target | 1) Outcome | 1) Indicator | 1) Target | 1) Main Impact | 1) Indicator | 1) Target
2) Output | 2) Indicator | 2) Target | 2) Outcome | 2) Indicator | 2) Target |  | 2) Indicator | 2) Target
3) Output | 3) Indicator | 3) Target | 3) Outcome | 3) Indicator | 3) Target
4) Output | 4) Indicator | 4) Target | 4) Outcome | 4) Indicator | 4) Target
| Qualitative |  |  | Qualitative |  |  | Qualitative
5) Output | 5) Indicator | 5) Target | 5) Outcome | 5) Indicator | 5) Target |  | 1) Indicator | 1) Target
| Quantitative |  |  | Quantitative |  |  | Quantitative
6) Output | 6) Indicator | 6) Target | 6) Outcome | 6) Indicator | 6) Target | 2) Main Impact | 1) Indicator | 1) Target
7) Output | 7) Indicator | 7) Target | 7) Outcome | 7) Indicator | 7) Target |  | 2) Indicator | 2) Target
| Qualitative |  |  | Qualitative |  |  | Qualitative
8) | 8) Indicator | 8) Target | 8) Outcome | 8) Indicator | 8) Target |  | 1) Indicator | 1) Target
| Quantitative |  |  | Quantitative |  |  | Quantitative
9) Output | 9) Indicator | 9) Target | 9) Outcome | 9) Indicator | 9) Target | 3) Main Impact | 1) Indicator | 1) Target
| Qualitative |  |  | Qualitative |  |  | Qualitative
10) Output | 10) Indicator | 10) Target | 10) Outcome | 10) Indicator | 10) Target |  | 1) Indicator | 1) Target
Note: Please add/subtract number of "results, indicators and targets" as needed by incerting or deleting rows A few complementary indicators for each result step are in most cases sufficient.
Result Level 1
Activities are carried out as planned
Result Level 3
Target groups accept offer
Result Level 7
Intervention/Society changes
Result Level 2
Target groups are reached
Result Level 4
Target groups change their attitudes and/or develop new skills
Result Level 6
The target groups' living conditions change
Result Level 5
Target groups change their behavior

## Logframe Template
LogFrame for Monitoring Purposes
Results | result indicators | indicators' definition/ calculation mode | measurement frequency | baseline | current value/ latest value available |  | project target | sources & methods of info (means of verification) | who collects the data (roles & functions)
|  |  |  | value/ ref. date | value / date | value / date
Project Impact: | Indicators
[specify here] | Indicator 1 [specify here]
Project outcome 1 | indicator 2
indicator 3
Project outcome 2 | indicator 4
indicator 5
etc.
Example: |  |  |  | 2022-03-01 | 2022-08-01 | 2022-11-01 | End-Date Targets
Outcome 1: communication between patients and health workers becomes more effective | 1. ratio of interviewed patients who can describe received diagnosis in the same way as reported in the health card | # interviewed patients with answer (1) for Q13 of the interview questionnaire / total # interviewed patients | bi-annually | 20% | 25% |  | 90% | post-consultation interviews with patients | project M&E specialist
| 2. ratio of interviewed patients who can describe the prescribed treatment in the same way as reported in the health card | # interviewed patients with answer (1) for Q14 of the interview questionnaire / total # interviewed patients | bi-annually | 15% | 15% |  | 90% | post-consultation interviews with patients | project M&E specialist
| 3. ratio of interviewed patients who can describe the criteria to come back to the health facilities as specified in the health card | # interviewed patients with answer (1) for Q15 of the interview questionnaire / total # interviewed patients | bi-annually | 30% | 25% |  | 90% | post-consultation interviews with patients | project M&E specialist
| 4 degree of interviewed patients' satisfaction with the medical consultation | # interviewed patients with answer (1) for Q16 of the interview questionnaire / total # interviewed patients | bi-annually | 45% | 50% |  | 90% | post-consultation interviews with patients | project M&E specialist
Note: some interractive data visualisation can be easily created based on below numbers, automatically updatable

## Theory of Change Example
Theory of Change Template - Defining Project Logic
Defining goals and the path to reach them
1a | 2b | 3c | 3c | 3b | 3a | 2 | Recommended order to complete: Step 1: Team first defines: (a) the problem the team is solving, (b) who is the target audience and (c) how they would reach that audience. Step 2: The team then develops their long-term vision for change - focus on the goal, then work backwards" Step 3: The team then works backwards from the vision to: (a) define benefits / project outcomes of the work (b) define services or products / project outputs (c) define activities that are needed to bring about change
What problem we are trying to solve? | Who is our key audience? | What is your entry point to reach your audience? | What steps or activities are needed to generate the services or products? | What are the services and products leading to those benefits/ outcomes? (Project outputs)? | What are the wider benefits of your work (Project outcomes)? | What is the long-term change you see as your goal (Project impact)?
MSF lacks skills/ experience to design, install, maintain and monitor solar oxygen systems | Clinic/hospitals medical staff; technicians (logs?) | Pilot sites in Gulu region; Dakar as hub | Market insights, procurement expertise, and technical knowledge developed through pilot testing and trainings | MSF medical- and technical support staff across select MSF field hospitals and clinics are capable of procuring, installing and maintaining medical grade solar production systems | Increased skills & knowledge of the target group to design, maintain and monitor solar oxygen system | Medical staff and technical support staff across MSF field hospitals are trained and comfortable with solar produced medical oxygen, and promote transition from diesel-to solar produced oxygen
MSF lacks skills/ experience in solar oxygen systems feasibility and scalability & cost/benefit of solar over diesel* | Medical staff; Operational staff; Logistics staff; Procurement |  | Development of evidence based material through pilot testing in multiple contexts. | MSF staff is aware of and have access to business cases, cost-benefit analysis of solar produced oxygen vs diesel, feasibility study, implementation plans | Increased skills and experience of target group in solar oxygen system feasibility and scalability and cost benefit of solar over diesel | MSF standard processes, procurement, support systems, resources in place to support solar oxygen in LMICs
0% use of solar oxygen in hospitals and health facilities in the Gulu Region & monthly ruptures of oxygen supply | Medical staff; Operational staff; Procurement |  |  | Increased use of solar oxygen in the pilot hospitals | Reduced environmental footprint; Reliable supply of medical grade oxygen | Broad adoption of solar oxygen in target hospitals / health centers, regions that improves patient outcomes through greater availability
Safety is a big concern as fuel trucks are often attacked | Logistics staff; Procurement |  | Pilot cases showcasing solar production as an alternative to diesel and other fossil fuels | Reduced fuel supplied to facilities | Reduction in # fuel truck visits with a corresponding reduction of safety incidents | MSF medical interventions are safe
The carbon footprint of the MSF intervention is negative (supplied by trucks, operating on fuel, wasting OC produced) | Operational staff; Logistics staff; Procurement |  |  | Reduced fuel supplied to facilities; Reduced oxygen wasted | Reduction in diesel volume; Reduction in carbon footprint; Greening MSF, positive signal | MSF oxygen interventions are carbon neutral - Onsite sustainable and reliable production of medical grade oxygen
Key Assumptions:
*1 oxygen concentrator of 5L could use 125L of diesel per month (around 3000€ per year) | Decision makers involved who will make the decision to switch from diesel to solar oxygen | Identified pilot site(s) accepts transition to solar oxygen production | The project plan is carried out as intended by the team and stakeholders | Assumes positive business case; availability of components, budget and resources for training
The identified lack of skills and experiences with solar oxygen is identical across the movement | N/A | Identified pilot site(s) have resources to aid the pilot tersting | Funding is available to support implementation of tasks | Data is provided by the project stakeholders according to the metrics developed | Solar oxygen is scaled across the movement
What is the problem / issue with the situation today that is critical enough to merit investment in the project; describe the scale and scope of the problem? | Who are the target audiences (may be multiple audiences)? | How will the project reach those audiences? | What type of activities or interventions will lead to the outputs and outcomes identified as preconditions for achieving the output and then outcomes? | What are the outputs (results) that are measurable, specific/ tangible enough to understand what the product or change would be exactly about? | What are clear benefits for the target groups? | Identify the desired long-term goals / vision; should be clear, realistic and definite.
Step 1
Step 3
Step 2

## Metrics Example
Transformational Investment Capacity Project Metrics Framework
Project Name: | Solar Oxygen Production |  |  |  | Solar Oxygen Production
Problem Statement: | Patients with respiratory infections are at risk due to none/limited access to medical grade oxygen |  |  |  | Patients with respiratory infections are at risk due to none/limited access to medical grade oxygen
Project Objective: | Pilot solar production medical grade oxygen system at Gwoza Hospital with the potential of global scale to ensure all patients with respiratory infections are treated |  |  |  | Pilot solar production medical grade oxygen system at Gwoza Hospital with the potential of global scale to ensure all patients with respiratory infections are treated
Target Groups (users) | MSF Hospitals and Health Facilities with treatment of medical grade oxygen located in emergency zones with fuel restrictions and/or limited access |  |  |  | MSF Hospitals and Health Facilities with treatment of medical grade oxygen located in emergency zones with fuel restrictions and/or limited access
Development/revision date: | Draft 0.1 |  |  |  | Draft 0.1
Project Baseline
Output Baseline |  |  | Outcome Baseline |  |  | Impact Baseline
MSF has no/limited knowledge and experience with design, installation, maintenance and performance of solar produced medical oxygen plants/systems |  |  | 100% of hospitals and health facilities in the Region are dependent on fuel supply and traditional generators |  |  | Current systems compromise quality of medical care at the societal level
MSF has no/limited knowledge and experience regarding the feasibility and scalability of solar produced medical oxygen plants/systems |  |  | 65% of hospitals and health facilities in the Region are having monthly ruptures of oxygen supply |  |  | Current systems contribute to negative environmental impact
|  |  | 1 oxygen concentrator of 5L use 125L of diesel per month (around 3000€ per year) |  |  | Current systems impose safety risks to hospital personal
Safety is a big concern as fuel trucks are often attacked
The carbon footprint of the MSF intervention is negative (supplied by trucks, operating on fuel, wasting OC produced
Outputs (Results of project activities) |  |  | Outcomes (results of project outputs) |  |  | Impact (Results of project outcomes when scaled)
Offerings |  |  | Results at the Target Group Level |  |  | Results at the Intervention/Societal Level
RESULTS What you do or offer in your project (and the people you reach) | INDICATORS | TARGETS | RESULTS (What you want the project to achieve within your target groups) | INDICATORS | TARGETS | The contribution you want to make with the project at the societal level | INDICATORS/PROXIES | TARGETS
1) Supplier of solar oxygen system identified and contracted 2) Production system designed and approved 3) Production system procured, assembled and tested 4) Production system is available on pilot site | Quantitative |  | 1) MSF staff is interested in solar powered oxygen production 2) MSF staff are able to use and maintain the system | Quantitative |  | Impact 1: MSF medical intervention improved | Quantitative
| 1) Supplier contract signed 2) System design sign-off by MSF 3) Goods receipt and testing report available 4) In country goods receipt signed | 1) Contract by Q2 2022 2) System approved by Q3 3) Production system ready for shipping end Q4 2022 4) Production system onsite Q1 2023 |  | 1) Number of staff/other hospitals interested in solar powered oxygen production 2) Number of MSF staff who are able to use and maintain solar powered oxygen production | 1) < 10 requests received 2) Minimum 2 MSF staffs at each hospital are able to use and maintain the system | a) MSF patients in LMICs have access to sustainable and reliable oxygen threatment b) Mortality caused by respiratory infections in LMICs is reduced c) Broad adoption of solar produced medical grade oxygen in government controlled hospitals, health centres, regions etc. | a) Number of MSF patients/people having access to sustainable and reliable oxygen treatment in LMICs b) Reduction in deaths caused by respiratory infections in LMICs c) Adoption rate per region/country | a) < 50% of people in LMIC have access to sustainable and reliable oxygen treatment b) 20% reduction in Reduction in deaths caused by respiratory infections in LMICs c) < 30 % of medical grade oxygen is produced by Solar
| Qualitative |  |  | Qualitative |  |  | Qualitative
| Red/Yellow/Green on overall project and on project scope, timeline and budget | Project status is Green by end of each quater |  | Other hospitals and health facilities are showing interest in the project | Thw other hospitals show interest in installing solar oxygen |  | 1) Medical- and technical field staff across MSF hospitals are trained and comfortable with solar produced medical oxygen.
5) Production system and maintenance tools are installed at pilot site 6) MSF staff trained in use and maintenance of the production system 7) KPI and monitoring system developed 8) Monitoring reports and final report with future recommendations 9) Pilot patients have access to solar produced medical grade oxygen 10) Pilot patients are treated with solar produced medical grade oxygen | Quantitative |  | 3) The hospital is able to maintain the oxygen production and storage system 4) The hospital can afford the operational cost of the production and storage system 5) The hospital does not have safety issues with supply of energy 6) The hospital are able to operate day/night | Quantitative |  | Impact 2: MSF medical intervention is carbon neutral | Quantitative
| 5) Installation report signed by MSF 6) Training certificates issued 7) KPI and monitoring system completed 8) Monitoring reports and final report with future recommendations completed 9) Number of patients having access to solar produced medical grade oxygen during the project 10) Number of patients treated with solar produced medical O2 during the project | 5) by Q1 2023 6) by Q1 2023 7) by Q1 2023 8) by Q2 2023 9) 80% of pilot patients have access to oxygen 10) 100 % of pilot patients in need of oxygen are treated |  | 3) Number of hours the system is non-operational/unable to produce oxygen 4) % of cost increase/decrease compared to baseline 5) % of reported safety issues compared to baseline (increase/decrease) 6) Number of operational hours in a day | 3) > 20% downtime 4) >/= to current operational costs 5) No safety issues reported 6) The system is operational 24/7 | a) Medical grade oxygen in MSF operations is produced from sustaiable energy sources | 1) Reduction of MSF carbon emmisions from health operations 2) % of medical grade oxygen volumes produced from clean energy vs fossil fuels | 1) < 5 % reduction 2) < 70%
| Qualitative |  |  | Qualitative |  |  | Qualitative
| Pilot patients and hospital staff are satisfied with the development of the pilot and the oxygen system (Survey) |  |  | 1) The hospitals technical and medical staff are satisfied with the system and experience increased efficiency in operations 2) Patients are experiencing less waiting and/or improved treatment outcomes | Patients and hospital staff are satisfied with the system and experience improved treatment outcomes (survey, post implementation interviews)
11) Trained MSF staff are able to use and maintain the pilot system 12) The hospital staff is satisfied with the training and the pilot system 13) Patients are satisfied with the treatment provided during the project | Quantitative |  | 7) MSF hospitals and health facilities have antonomous supply of solar produced medical oxygen 8) MSF hospitals and health facilities have sustainable and reliable supply of medical oxygen 9) The hospital is able to treat all patients in need of medical grade oxygen | Quantitative |  | Impact 3: MSF medical intervention is safe | Quantitative
| 11) Hours of oprational downtime 12) Number of hospital staff that are satisfied with the training and the pilot system 13) Number of patients satisfied with the the treatment provided during the project | 11) Operational 24/7 12) <80% satisfaction 13) <80% satisfaction |  | 7) Number of MSF hospitals and health facilities with antonomous supply of solar produced medical oxygen 8a) Number of times the hospital was depending on outside energy supply 8b) Number of ruptures in medical oxygen supply 9) Number of patients treated compared to number of patients in need | 7) 20% by 2023 8a) > two times per year 8b) No ruptures in medical oxygen supply 9) 100% of patients in need of medical grade oxygen treated | a) Supplying energy to MSF hospitals and health clinics in LMICs is safe and does not pose a risk to personal | 1) Reduction in safety incident reports | 1) No safety issues reported
| Qualitative |  |  | Qualitative |  |  | Qualitative
| Positive feedback from project stakeholders (patients, hospital staff, supplier etc.) |  |  | 1) Hospital staff feel empowered and able to treat pattients according to medical needs 2) Patients experience improved treatment outcomes |  |  | 1) Staff members and personal feel safe working with solar oxygen production at MSF hospitals and health facilities | The majority of personal feel safe working for/with MSF
Result Level 1
Activities are carried out as planned
Result Level 3
Target groups accept offer
Result Level 7
Intervention/Society changes
Result Level 2
Target groups are reached
Result Level 4
Target groups change their attitudes and/or develop new skills
Result Level 5
Target groups change their behavior
Result Level 6
The target groups' living conditions change