## 00 Introduction
Introduction & Objectives
To efficiently track project progress and to ensure final objectives are met through preventive and corrective actions, TIC projects are recommended to establish a M&E framework including metrics composed of baselines, output/outcome results and indicators for each of the seven result levels (see Result Staircase to the right). The purpose of the TIC Metrics is to serve as an aid to TIC project teams in establishing and measuring the progress, outcome and impact of their transformational projects from the point of entry to project completion and beyond. Steps to complete the TIC Metrics Framework: 1) Familiarize yourself with the TIC Metrics Framework by reading this Introduction sheet and consult the TIC Metrics Guideline as required. The guideline includes detailed information on the framework including resources such as commonly used terms, examples of KPIs, checklists and references. 2) Complete the Theory of Change template (planning tool) When: upfront for the proposal 3) Complete the TIC Metrics Template (tracking project progress and impact tool) When: Upfront or near the beginning of the project 3a) Develop results and indicators for each of the results steps - plot them in the appropriate sections of the TIC Metrics Template 3b) Develop baselines for the 3 main result levels (Output, Outcome, Impact) using the indicators and qualitative observations - plot them in the appropriate sections of the TIC Metrics Template. 4) Complete the Monitoring LogFrame Template (detailed tracking and monitoring tool) When: first 6 month of the project (team in place) 4) Work backwards and forwards through the models to validate the logic of sequences - ensure relation between indicators, targets and baselines. |  |  |  | Result Staircase
The TIC Metrics Framework
The TIC Metrics Framework consist of four components: the Result Staircase the Theory of Change Template, the Metrics Template and the Monitoring LogFrame. The models are described below and the templates including examples are available as separate sheets within this document (Template sheets are green, Examples are blue). 1. The Theory of Change The purpose of the Theory of Change model is to develop the project's basic rational and logical framework to ensure a plausible relation between inputs and impact. Theory of Change is essentially a comprehensive description and illustration of how and why a desired change is expected to happen in a particular context. It is particularly focused on mapping out or “filling in” what has been described as the “missing middle” between what a project or change initiative does (its activities or interventions) and how these lead to desired goals being achieved. It does this by first identifying the desired long-term goals and then works back from these to identify all the conditions (outcomes) that must be in place (and how these related to one another causally) for the goals to occur. 2. The Result Staircase The purpose of the result staircase is to provide a model enabling projects to be able to focus on specific targets at any given point while maintaining a complete overview of how project activities, outputs, outcomes and impact are interlinked and continuously affect one another. There are numerous levels at which project impact can be achieved. These levels of effect are illustrated using the results staircase, step 1-7. While Large-Scale Projects will use all 7 steps, Incubator Projects may only use the 3 main result levels. A project offers certain services and products. These are "Outputs". Because of these outputs, results are produced within the target groups. These are "Outcomes". These outcomes can be of various kinds may provide results at the society level. These are "Impact".
Result Level |  | Step | When | Description
OUTPUT (project) | Output Level - Targets and Indicators | 1 | Activities are carried out by the project within its lifespan | Impact and outcomes result from the products produced or services provided by a project. These products or services are Outputs. They are not themselves results; they are prerequisites for achieving results on higher levels (outcomes and Impact).
|  | 2 | The target groups are reached (service or product received)
|  | 3 | The target groups accepts the offer (service or product). Level 3 is considered a bridge to outcomes.
OUTCOME (Target group) | Result Level - Target and Indicators | 4 | The outcome level is reached when we observe changes in attitudes and/or knowledge and skill levels within the target group | Results within the target group are Outcomes. What benefits does the project have for the target group, and what changes is it intended to bring about? Outcomes always refer to results within the project target group and can be further divided, as seen at levels 4 - 6 in the result staircase (and to the left). Successful outcomes will contribute to changes at the intervention/societal level. Projects can have multiple outcomes addressing the same desired change (the final goal).
|  | 5 | The outcome level is reached when we observe changes in behavior within the target group
|  | 6 | The outcome level is reached when the target group's circumstances change, and members are able to improve their living conditions.
IMPACT (Society) | Result Level - Target and Indicators | 7 | The outcome level is reached when larger populations are affected by the changes driven by the project (social, economic, etc.) | Results at the intervention/societal level are "impact" (as shorthand for social impact). Impact describe the long-term results that are achieved or influenced by the project. These societal-level objectives are closely linked to the organization’s vision. Impact always relates to a part of the society as a whole, for instance the population in the district of a city or within a specific region. TIC projects are to develop targets and indicators for long term impact and include the responsibility of monitoring and reporting in TIC Completion Report (Transition to Business as Usual section) upon project accomplishment.
3. The TIC Metrics The purpose of the TIC Metrics is to provide a model enabling TIC projects to identify and track project targets and impact through use of baselines and indicators. Following the logic of the Result Staircase; "Results" and "Indicators" as well as their "Baselines" and "Targets" are developed for each of the three main result levels (Output, Outcome and Impact) by using the TIC Metrics Template. For Large-Scale Projects, results and indicators are further categorized as per the seven result levels of the Result Staircase. It is recommended to first develop the Results and Indicators e.g., what you want to achive and what you would like to measure, and subsequently develop the baselines (initial values of the indicators) and the targets (desired values at a certain point e.g., at gate 1, end of year, end of project). The TIC Metrics Template depicts the logic of your Theory of Change model and the results staircase in which input is found at the bottom, impact at top. The same logic holds for the TIC Metrics Template where outputs are defined on the left side and impact on the right. Each step (from left to right-top down) is based on the one preceding it. The model is flexible and approached in multiple directions e.g. right-left/bottom-top (working backward approach) and subsequently for plausibility check left-right/top-down to ensure a logic and impact oriented approach. The focus here is on the if-then relationships between the individual steps - If you succeed in moving to the end in both directions without mishap, you have a logical impact metrics model.
Plausibility Check – from inputs to impact
Level 1 | If the necessary resources (inputs) are available, the planned activities can begin and the offerings or products can be created
Level 2 | If the offerings and the products are available, they can be used by the target group
Level 3 | If the offerings and the products are used, then the prerequisite for participant satisfaction is met
Level 4 | If the participants are satisfied with the offering, then the prerequisite has been met for the desired changes in target-group knowledge and attitudes to be effected
Level 5 | If the desired changes in target-group knowledge and attitudes have been effected, this creates the possibility that they will act differently
Level 6 | If members of the target group act differently, then their living conditions may change
Level 7 | If participants’ living conditions change, then this contributes to changes at the societal level
4. The Monitoring LogFrame The purpose of the Monitoring LogFrame is to provide TIC teams with a standard template to systematically track and monitor project progress on regular basis (weekly, monthly, quarterly). The tool is used by project teams to collect, manage and analyse information in order to update the TIC Metrics, and to inform preventive and corrective measures. The tool provides the ability to extract trends over time for each of the indicators and against comparators (baseline, target), details on what data collection tools are to be used on each indicator, calculation methods, frequency, etc.
Points to consider before getting started
1. Develop a clear problem analysis at the baseline, explaining what the problem to be addressed is and how its root causes are considered in the development of the project strategy.
2. It is recommende to first develop the project results at the Output/Outcome/Impact levels, then their indicators and targets, and finally the baselines.
3. Developing solid baselines to measure against is essential for a strong M&E framework. Baseline data is developed from the same indicators used to track future results. Baselines may be supported by qualitative obseevations and testimonials.
4. When developing indicators, consider carefully what you would like to measure. A few complementary indicators for each result step are in most cases sufficient
5. Indicators are not carved in stone and should be reviewed frequently to ensure alignment with the projects progress and desired impact
6. Establishing precise indicators can be challenging but everything is measurable. It is better to have indicators based on quality assumptions or proxi indicators than having no indicators
7. Indicators and their baseline and target values should be developed in collaboration with project stakeholders
8. The TIC Metrics Framework is based on a people centered approach where results and indicators are based on behavioral change. It is therefore advised to formulate results and indicators according to the change in the target group(s) e.g. Patients, MSF staff, health workers.

## Theory of Change Template
Theory of Change Template - Defining Project Logic - Incubators
Defining goals and the path to reach them
1a | 1b | 3 | 2 | Recommended order to complete: Step 1: Team first defines: (a) the problem the team is solving, (b) who is the target audience and how they would reach them. Step 2: The team then develops their long-term vision for change - focus on the goal, then work backwards" Step 3: The team then identifies interim steps to head towards to long-term goal, focusing on the scope of the current project. This may includes activities, outputs or benefits/outcomes of the work.
What problem are we trying to solve? | Who is our key audience and how do we reach them? | How will the project achieve an interim step towards that long-term vision (activities, outputs, benefits/outcomes)? | What is the long-term change you see as your goal (Project impact)?
Key Assumptions:
What is the problem / issue with the situation today that is critical enough to merit investment in the project; describe the scale and scope of the problem? | Who are the target audiences (may be multiple audiences)? How will the project reach those audiences? | What type of activities or interventions will lead to the outputs and outcomes identified as preconditions for achieving the output and then outcomes? What are clear benefits for the target groups? | Identify the desired long-term goals / vision; should be clear, realistic and definite.
Source: Capgemini Transformaion
Step 1
Step 3
Step 2

## Metrics Template
Transformational Investment Capacity Project Metrics Framework - INCUBATOR
Project Name:
Problem Statement:
Project Objective:
Target Groups (users)
Development/revision date:
Project Baseline
Output Baseline |  |  | Outcome Baseline |  |  | Impact Baseline
Outputs (Results of project activities) |  |  | Outcomes (results of project outputs) |  |  | Impact (Results of project outcomes when scaled)
Offerings |  |  | Results at the Target Group Level |  |  | Results at the Intervention/Societal Level
RESULTS What you do or offer in your project (and the people you reach) | INDICATORS | TARGETS | RESULTS (What you want the project to achieve within your target groups) | INDICATORS | TARGETS | The contribution you want to make with the project at the societal level | INDICATORS/PROXIES | TARGETS
| Quantitative |  |  | Quantitative |  |  | Quantitative
1) Output | 1) Indicator | 1) Target | 1) Output | 1) Indicator | 1) Target | 1) Output | 1) Indicator | 1) Target
2) Output | 2) Indicator | 2) Target | 2) Output | 2) Indicator | 2) Target | 2) Output | 2) Indicator | 2) Target
3) ... | 3) ... | 3) … | 3) ... | 3) ... | 3) … | 3) ... | 3) ... | 3) …
| Qualitative |  |  | Qualitative |  |  | Qualitative
4) Output | 4) Indicator | 4) Target | 4) Output | 4) Indicator | 4) Target | 4) Output | 4) Indicator | 4) Target
5) ... | 5) ... | 5) ... | 5) ... | 5) ... | 5) ... | 5) ... | 5) ... | 5) ...
Note: Please add/subtract number of "results, indicators and targets" as needed by incerting or deleting rows A few complementary indicators for each result step are in most cases sufficient.
Result Level - Outputs
Activities are carried out as planned. Target groups are reached and accepts the offer
Result Level - Impact
Intervention/Society changes
Result Level - Outcomes
Target groups change their attitudes/develop new skills, the behavior or their living conditions change

## Logframe Template
LogFrame for Monitoring Purposes
Results | result indicators | indicators' definition/ calculation mode | measurement frequency | baseline | current value/ latest value available |  | project target | sources & methods of info (means of verification) | who collects the data (roles & functions)
|  |  |  | value/ ref. date | value / date | value / date
Project Impact: | Indicators
[specify here] | Indicator 1 [specify here]
Project outcome 1 | indicator 2
indicator 3
Project outcome 2 | indicator 4
indicator 5
etc.
Example: |  |  |  | 2022-03-01 | 2022-08-01 | 2022-11-01 | End-Date Targets
Outcome 1: communication between patients and health workers becomes more effective | 1. ratio of interviewed patients who can describe received diagnosis in the same way as reported in the health card | # interviewed patients with answer (1) for Q13 of the interview questionnaire / total # interviewed patients | bi-annually | 20% | 25% |  | 90% | post-consultation interviews with patients | project M&E specialist
| 2. ratio of interviewed patients who can describe the prescribed treatment in the same way as reported in the health card | # interviewed patients with answer (1) for Q14 of the interview questionnaire / total # interviewed patients | bi-annually | 15% | 15% |  | 90% | post-consultation interviews with patients | project M&E specialist
| 3. ratio of interviewed patients who can describe the criteria to come back to the health facilities as specified in the health card | # interviewed patients with answer (1) for Q15 of the interview questionnaire / total # interviewed patients | bi-annually | 30% | 25% |  | 90% | post-consultation interviews with patients | project M&E specialist
| 4 degree of interviewed patients' satisfaction with the medical consultation | # interviewed patients with answer (1) for Q16 of the interview questionnaire / total # interviewed patients | bi-annually | 45% | 50% |  | 90% | post-consultation interviews with patients | project M&E specialist
Note: some interractive data visualisation can be easily created based on below numbers, automatically updatable

## Theory of Change Example
Theory of Change Template - Defining Project Logic - Incubators
Defining goals and the path to reach them - BLUST
1a | 1b | 3 | 2 | Recommended order to complete: Step 1: Team first defines: (a) the problem the team is solving, (b) who is the target audience and how they would reach them. Step 2: The team then develops their long-term vision for change - focus on the goal, then work backwards" Step 3: The team then identifies interim steps to head towards to long-term goal, focusing on the scope of the current project. This may includes activities, outputs or benefits/outcomes of the work.
What problem are we trying to solve? | Who is our key audience and how do we reach them? | How will the project achieve an interim step towards that long-term vision (activities, outputs, benefits/outcomes)? | What is the long-term change you see as your goal (Project impact)?
Vaccines lose potency if not maintained at the correct temperature, potentially jeopardizing immunization programs and public health outcomes. | Medical staff, Logistics staff | Blust design with thermal insulation materials. Interior structure that coducts the cold from the CU to the TU. Display and alarm when the device interior is outside of the temperature range (2-8ºC). Training of staff on contingency plan in case of cold chain breakdown. | Vaccination campaigns are carried out without delays nor obstacles, covering and giving aid to populations at risk of preventable diseases.
Accurate and timely diagnostics rely on the safe transport of temperature-sensitive reagents and biological samples, which isn't currently guaranteed. | Medical staff, Logistics staff | Blust design with thermal insulation materials. Interior structure that coducts the cold from the CU to the TU. Display and alarm when the device interior is outside of the temperature range (2-8ºC). Training of staff on contingency plan in case of cold chain breakdown. | Guaranteeing diagnostic accuracy and timely responses during outbreaks in all contexts.
Many life-saving medications require strict temperature control to remain effective. Currently MSF staff can't assure that they are met when going to peripheral communities. | Medical staff, Logistics staff | Blust design with thermal insulation materials. Interior structure that coducts the cold from the CU to the TU. Display and alarm when the device interior is outside of the temperature range (2-8ºC). Training of staff on contingency plan in case of cold chain breakdown. | Operations are carried out efficiently, with no cold chain breakdowns. No cold chain material is damaged thus resources and medicatoins aren't wasted or thrown away.
Dependency of current PCC* on Ice Packs that require freezers, which are challenging to operate in areas with inconsistent or absent electrical power. | Logistics staff | Solar energy compatibility for operations in off-grid environments. UC has wide range of input voltage (110V to 240V) to be able to recharge in any region. | MSF cold chain campaings don't solely rely on stable electrical power. Reduced environmental footprint.
Dependency of current PCC* on Ice Packs that can cause freezing temperatures, damaging sensitive items, or allow overheating if poorly conditioned. | Medical staff | Blust has ice packs of Phase Changing Material (PCM) at 4ºC. They require less energy to freeze than water ice packs and there is no risk of freezing since the phase change happens at a higher temperature. There is also no need to condition the PCM icepacks so there is no option of overheating nor freezing. | Operations are carried out efficiently, with no cold chain breakdowns. No cold chain material is damaged, thus resources and medicatoins aren't wasted or thrown away.
The current PCC* have small storage capacity so users need multiple devices to be able store everything. | Medical staff, Logistics staff, Procurement | More storage capacity in Blust and less devices are needed because 1 CU can refrierate multiple TU. | Minimizing the number of cold chain devices used in a campaign.
The current PCC* have limited autonomy and need frequent re-cooling cycles that reduce operational efficiency and increase reliance on freezers. | Medical staff, Logistics staff | Blust's CU solar-powered option allows to refrigerate the TU in off-grid settings. The CUs can be easily transported and installed in intermediate locations to extend autonomy since they are also lightweight. | Autonomy sustained in MSF operations becomes 21-30 days, supported by intermediate charging phases.
The current PCC* and Indigo devices are difficult to dispose of. It's difficult to find local waste management facilities that can recycle and treat the devices at its end of life. | Logistics staff | Blust is designed with the whole life cycle in mind so that it’s a sustainable device. At its end of product life, it can be disassembled easily for the waste management. The CU is optimized to use the minimum plastic as possible and instead uses aluminum so that it can be reused and recycled in local waste management facilities. | Reduced environmental footprint. Disposal of waste in local facilities, reduction of the need to export it to another country's facility.
The charger of Indigo, an ice-pack free alternative, emits loud noise during the 4 to 6 hours that it’s charging which causes discomfort to the team that is working in the same room | Medical staff, lab technicians, Logistics staff that are working in the same room as the charger. | The CU uses thermoelectric cooling that emits minimal noise. | MSF staff work under better conditions.
During charging, interior surfaces of the Indigo charger are hot enough to cause burns. There is risk of burns if the charger is opened before it has had sufficient time to cool. Cooling takes one to two hours. | Medical staff, Logistics staff | The CU is designed to dissipate heat. The thermoelectric cooler doesn't get as hot as the Indigo charger. | MSF medical interventions are safe. Minimize risks.
Indigo charger is very heavy. MSF staff have difficulty when transporting it. | Medical staff, Logistics staff, Procurement | Lightweight, ergonomic and compact dimensions for ease of transport in remote areas. | Improve portability and comfort of cold chain devices.
Heat generated during charging of Indigo further complicates usage in hot climates. | Medical staff, lab technicians, Logistics staff that are working in the same room as the charger. | The CU is designed to dissipate heat. The thermoelectric cooler doesn't get as hot as the Indigo charger. | MSF staff work under better conditions.
Key Assumptions:
*PCC= Passive cold chain devices. Includes vaccine carriers and cold boxes (RCW25). | MSF staff operate in diverse and often challenging environments where infrastructure is limited or unreliable. For example, areas with unstable or no electrical power. | Taking into consideration the V0 prototype characteristics. | Assumess positive business case; availability of components, budget and training on how to use Blust.
The contexts in which the PCC is used have unstable and unreliable power sources. |  | The project plan is carried out as intended by the team and stakeholders.
The contexts in which the PCC is used have high temperature conditions. |  | Funding is available to support implementation of improvements.
Some of the contexts use Indigo ice-free cold chain device.
What is the problem / issue with the situation today that is critical enough to merit investment in the project; describe the scale and scope of the problem? | Who are the target audiences (may be multiple audiences)? How will the project reach those audiences? | What type of activities or interventions will lead to the outputs and outcomes identified as preconditions for achieving the output and then outcomes? What are clear benefits for the target groups? | Identify the desired long-term goals / vision; should be clear, realistic and definite.
Source: Capgemini Transformaion
Step 1
Step 3
Step 2

## Metrics Example
Transformational Investment Capacity Project Metrics Framework - INCUBATOR
Project Name: | Patient Centred Digital Therapeutics for Diabetes and TB
Problem Statement: | Chronic conditions such as Diabetes and TB/MDR-TB require protracted treatment interventions demanding patient-centred support for sustained patient understanding, motivation and behaviour change. This patient centred model is insuffiently delivered within the current model contributing to sub-optimal patient experience, treatment outcomes, and adverse effects.
Project Objective: | Within 18-months co-create and pilot patient centred DTx platforms for Diabetes and TB in Lebanon, India, and Belarus and disseminate associated insights and evidence on process and impact.
Target Groups (users) | Patients living with Type 1 and Type 2 Diabetes treated in the MSF clinic in the Bekaa Valley Lebanon; Patients living with and being treated for TB/MDR-TB in the MSF Clinic Mumbai, India and those in the MSF supported hospital in Minsk, Belarus; All relevant associated clinicians in these project locations (including nurses, doctors, mental health practitioners)
Development/revision date: | October 2022 version 1.0 - Updated by Hanna Phelan
Project Baseline
Output Baseline |  |  | Outcome Baseline |  |  | Impact Baseline
MSF has limited/no knowledge and experience with the design, implemention, maintenance and evaluation of DTx for patients living with and being treated for Diabetes and TB/MDR-TB |  |  | Approximately 50% of patients living with diabetes treated in Bekaa Valley clinics are living with uncontrolled conditions partially associated with sub-optimal condition understanding, mediciation adherence, and confidence self-managing. |  |  | Current systems insuffiently integrate evidence based digital health and digital therapeutic interventions to meet demand
MSF has limited/no knowledge and experience regarding the feasibility and scalability of DTx interventions |  |  | Estimated that up to 56% of patients engaged in treatment for MDR-TB may be lost to follow up in settings such as India and Belarus |  |  | Current access to support and guidance between clinic visits is sub-optimal for patients being treated for diabetes/TB/MDR-TB in low resource and humanitarian settings
The Global health environment currently demonstrates very limited understanding of the feasibility, impact and scability of DTx interventions for Diabetes/TB/DR-TB in low resource and humanitarian settings |  |  | Increase and evolution of supportive patient-centred interventions essential in meeting mounting burden of complex conditons, scaling impact of MSF clinicians and avoiding clinician overwhelm |  |  | Mental wellbeing and psychosocial support is insufficient for the target patient cohort
Outputs (Results of project activities) |  |  | Outcomes (results of project outputs) |  |  | Impact (Results of project outcomes when scaled)
Offerings |  |  | Results at the Target Group Level |  |  | Results at the Intervention/Societal Level
RESULTS What you do or offer in your project (and the people you reach) | INDICATORS | TARGETS | RESULTS (What you want the project to achieve within your target groups) | INDICATORS | TARGETS | The contribution you want to make with the project at the societal level | INDICATORS/PROXIES | TARGETS
1) Needs assessment reports 2) Diabetes and TB patient platforms 3) Clinician dashboards 4) feasibility assessments 5) Pilot assessments 6) Sharepoint 7) Advocacy and communications materials | Quantitative |  | 1) Improved medication adherence 2) Increased self-management confidence 3) Improved condition understanding 4) Patient and clinician satisfaction with DTx intervention 4) Increased awareness and engagement of DTx across relevant MSF stakeholder groups | Quantitative |  | 1) Contribute to humanitarian and global health evidence of DTx for Diabetes and TB ​within MSF movement and to relevant stakeholders 2) To improve access to high quality patient centred care for patients living with TB and Diabetes in low-resource and humanitarian settings catalysed by integration of DTx | Quantitative
| 1) 3 Needs assessments conducted/summarised 2) 3 Patient platforms developed/adapted 3) 3 Clinician platforms developed/adapted 4) 3 Feasibility assessments conducted 5) 3 pilot assessments conducted 6) 1 sharepoint platform launched and maintained 7) minimum of 5 communications/advocacy materials (e.g. blogs, publications, conference presentations etc.) shared internally and externally | 1) Needs assessments all completed and summarised by end of Q2 2023 2) Version 3 iternations of all platforms developed by start of Q2 2024 3) Version 3 iternations of all platforms developed by start of Q2 2024 4) Feasibility assessments all conducted and summarised by start of Q4 2023 5) Pilot assessments conducted by Q2 2024 6) Sharepoint site launched by Q4 2022 7) Communications and Advocacy target met before end of Q2 2024 |  | 1) % increase compared to context baseline 2) % increase compared to self-reported baseline 3) % increase compared to pre-intervention pilot baseline 4) Post-pilot satisfaction 5) Coverage of requests for engagements (both educational and implementation scoping) in identified stakeholder groups/projects | 1-4) To be defined as a part of research protocol development for individual projects 5) 1 DirMed platform presentation; 2 working group presentations; 3 project scoping requests |  | 1) Publish/disseminate evidence generated 2) Scale-up DTx platforms for relvant patients in project locations and launch in other relevant projects | TBC
| Qualitative |  |  | Qualitative |  |  | Qualitative
| 1) Project progress green/yellow/red 2) Pilot patients and clinicians are satisfied with process and outputs | 1) Project status in green end of each quarter 2) Survey associated with each assessment period (feasibility and pilot) |  | 1) Patients and clinicians report perceived improvemement of patient centred quality of care | Survey/interview reported improvement |  | 1) MSF standard processes, procurement, support systems, resources developed and in place to support implementation of DTx in LMICs 2) Medical staff and technical support staff across MSF hospitals in the field are trained and comfortable with DTx interventions | 1) Material globally available in Arabic, English and French
Result Level - Outputs
Activities are carried out as planned. Target groups are reached and accepts the offer
Result Level - Impact
Intervention/Society changes
Result Level - Outcomes
Target groups change their attitudes/develop new skills, the behavior or their living conditions change